## Sheet1
WORK
6 | Project Planning Analysys
8 | CSC Fresher training Program : Site Branding
10 | Project Planning Analysys
11 - 13 | Project Requirements Practice
Research Model View Presenter
Site Branding Practice
Sharepoint Object Model & CAML Practice
14 -23 | Project Implementation
14 | Building Prerequisite Components (Column, List, Library...)
14 -16 | Building Site Layout
16 - 23 | Building Webparts
Building Home Page
Building All News Page
Building Update Page
Building Insert Page
Building Detail Page
23 | Final Deployment
23 | Perform UNIT Test
25 | Packaging Project